1. Sprint 1 System Functionality

At the end of Sprint 1, HealthQuest Wellness has a functioning foundation that supports user authentication, profile management, and client journaling. Both clients and therapists can register, log in, and manage their profiles. The therapist-client relationship can be established, and the UI has been prepared for clients to submit daily journal entries. The Firebase backend is fully operational and supports all data relationships required for future features. The application is not yet feature-complete but is stable enough for internal testing of the core user flows.

1.1 Implemented Features

The following features are fully implemented and functional at the end of Sprint 1:

- Firebase backend — database and authentication fully configured with appropriate relationships between clients, therapists, journals, and chat data

- Splash screen — displays the HealthQuest Wellness logo and branding on app launch

- User registration — both clients and therapists can create accounts via the sign-up flow (name, email, phone, date of birth, password)

- User login — clients and therapists can log in securely via Firebase Authentication

- Password reset — users can reset forgotten passwords via email

- Profile management — users can view and edit their profile information

- Therapist-client association — therapists can link their profile to assigned clients

- Journal page — UI for clients logging daily thoughts

1.2 Partially Implemented / Carried Over

The following features are partially implemented at the end of Sprint 1 and will be carried over to Sprint 2:

- Therapist journal comments — therapists can add comments to client journal entries; client receives a push notification

1.3 Not Implemented

The following features were not implemented at the end of Sprint 1 and will be carried over to Sprint 2:

- Account deletion — users can delete their accounts

2. Sprint 1 User Stories — Implementation Status

The table below lists all user stories planned for Sprint 1, their implementation status, and any notes or changes made during the sprint.

| ID | User Story | Size | Priority | Status | Notes / Changes |
| --- | --- | --- | --- | --- | --- |
| 1 | Therapist account creation | 3 | High | Done | N/A |
| 2 | Client account creation | 3 | High | Done | N/A |
| 3 | User profile editing | 2 | Medium | Done | N/A |
| 4 | Therapist-client association | 3 | High | Done | N/A |
| 5 | Firebase storage system setup | 5 | High | Done | N/A |
| 6 | Patient account deletion | 2 | Medium | Not Implemented / Carried Over | N/A |
| 7 | Password reset | 2 | Medium | Done | N/A |
| 9 | Journal page | 8 | High | Done | - focused on the UI initially as the AI model hadn’t yet been integrated |
| 23 | Splash screen | 2 | Low | Done | N/A |
| 24 | Therapist comments on journal entries | 5 | High | Partially Implemented / Carried Over | N/A |

Sprint 1 Planned Size: 35 points

Sprint 1 Actual Velocity: 28 points

3. Changes, Breakdowns, and New Stories

This section documents any modifications made to user stories during Sprint 1, any stories that were broken down further, and any new stories discovered during implementation.

3.1 User Story Changes

No changes made to user stories.

3.2 Stories Broken Down Further

No user stories were further broken down.

3.3 New User Stories Identified

The following new user stories were identified during Sprint 1 development:

| ID | User Story | Size | Priority | Added to backlog or implemented immediately? |
| --- | --- | --- | --- | --- |
| 25 | As a Therapist, I want the system to automatically generate a referral code so that I can share it with clients to ensure they are automatically linked to my profile during account creation or after | 3 | High | Added to backlog |

4. Lessons Learned

This section reflects on Sprint 1 as a team — what worked, what didn't, and what the team would do differently in Sprint 2.

| What went well | What didn't go as planned | What we'd do differently |
| --- | --- | --- |
| Implemented most of what was planned and we got a good view of what the app is going to look like | There were a few technical issues with one of our teammates that we didn’t account for so it slowed down development, but it was addressed as soon as possible | Account for more things possibly going wrong, but still prioritize the big parts of the app |
| Great communication between everyone. We made sure to always keep each other in the loop. And if we noticed something wrong or missing, we pointed it out | One of the user stories that was meant to be implemented in Sprint 1 wasn’t assigned to anyone, so it had to be carried into Sprint 2 | After selecting user stories, immediately turn them to GitHub issues so that we know everything is accounted for |

4.1 Team Reflection

Sprint 1 established a solid technical foundation and demonstrated strong team communication throughout the development process. The team successfully delivered most planned features despite an unexpected technical issue affecting one team member, which was resolved quickly and with minimal disruption. The main process gap identified was that one user story was not assigned to anyone before development began, resulting in it carrying over to Sprint 2. Going forward, the team has agreed to convert all sprint stories into GitHub issues with assigned owners immediately after sprint planning to prevent this from recurring.

5. Remaining Product Backlog

The following table lists all user stories yet to be implemented after Sprint 1, including updated pre- and post-conditions. Stories carried over from Sprint 1 are included here.

| ID | User Story | Size | Priority | Pre-conditions | Post-conditions |
| --- | --- | --- | --- | --- | --- |
| 6 | Account deletion | 2 | Medium | - account exists - user is signed in | - account has been deleted, but data is preserved for therapists |
| 8 | Daily journal notification | 3 | Low | - user has an account - user is signed in | - if user has not logged journal by 8pm, receive notice to log |
| 10 | Therapist views organized profile page | 3 | Medium | - profile page exists and contains organized fields | - client is logged in, selects button to view profile page |
| 11 | Therapist-client chat | 8 | High | - therapist is logged in - therapist has active clients - therapist opens chat page | - therapist sends message - client receives message |
| 12 | Therapist views deleted account info | 3 | Medium | - client deletes account - therapist is notified clients account has been deactivated | - therapist retains chat history with deleted clients, but is marked as a deactivated profile |
| 13 | Push notifications for crisis | 3 | High | - AI has been trained to detect crisis | - therapist is notified with a push notification in case of concerning information being detected |
| 14 | AI tracking for dangerous behavior | 8 | High | - AI has been trained to detect harmful information after client posts a journal or chat | - client is notified that their therapist has been contacted when something harmful is detected |
| 15 | Therapy-trained AI model | 8 | High | - client is logged in - AI model has been trained and implemented | - AI model is trained on medical data and responds appropriately to chat messages |
| 16 | Organized therapist chat page | 5 | Medium | - therapist is logged in - therapist opens chat page | - chat page is organized with timestamps and appropriate signifiers to distinguish between clients and therapists |
| 17 | Therapist-to-therapist messaging | 5 | Low | - therapist is signed in - therapist views other available care providers - therapist opens a new chat with care providers | - therapists sends message to another care provider - other care provider receives message |
| 18 | Client requests new therapist | 3 | Medium | - client is signed in - client opens profile page - client clicks the ‘select new care provider’ button and is shown a list of care providers and their credentials | - a new therapist is sent a notification requesting a new patient |
| 19 | Clear journal prompts for habits | 5 | Medium | - client is logged in - client opens journal page | - client is shown organized locations to log their daily habits, not just a text entry, with associated iconography |
| 20 | Client AI chat page | 5 | Medium | - client is signed in - client selects AI-specific chat page | - client sends AI message - AI responds to chat message |
| 21 | Accessibility / colorblind support | 3 | Low | - application and color scheme exist | - color scheme passes ADA requirements for contrast |
| 22 | Logo and color scheme | 3 | Low | - application UI exists | - clear and cohesive branding exists on the application |
| 24 | Therapist comments | 5 | High | - therapist is signed in - therapist views clients journals | - comment added to clients journal - client receives push notification that they have a pending comment for review from their provider |
| 25 | Therapist referral code generation | 3 | High | - therapist has an account - the database is set up | - a unique code is generated and stored in the database - code is visible to the therapist on their profile page - client is visibly associated with the therapist |

Remaining Backlog Size: 75

6. Sprint 2 Plan

Taking into account the pre- and post-conditions of the remaining stories and the team's velocity from Sprint 1, the following user stories are selected for Sprint 2. The cumulative size targets approximately 1/3 of the full backlog.

6.1 Selected Stories

| ID | User Story | Size | Priority | Rationale for inclusion |
| --- | --- | --- | --- | --- |
| 6 | Account deletion | 2 | Medium | It was a user story not implemented in Sprint 1, so it was carried over to Sprint 2 |
| 11 | Therapist-client chat | 8 | High | This is a core feature of the app. Enabling communication between a therapist and their client is important to the app’s overall value and effectiveness |
| 13 | Push notifications for crisis | 3 | High | This feature is integral to client safety, especially for critical situations. Addressing it early on means we give it enough time, resources, and energy to ensure it’s implemented properly |
| 14 | AI tracking for dangerous behavior | 8 | High | This feature enhances safety, and as we’re also focusing on the chat feature in this sprint, it aligns well with other user stories |
| 16 | Organized therapist chat page | 5 | Medium | We’re also introducing chat functionality in this sprint, so UI organization is necessary |
| 20 | Client AI chat page | 5 | Medium | This sprint focuses heavily on chat features and functionality, so developing this feature alongside features like the AI tracking system and page UI is logical |
| 24 | Therapist comments | 5 | High | Since we’re also introducing messaging, this feels like a natural extension of that to enhance therapist-client interaction |
| 25 | Therapist referral code generation | 3 | High | The app must have clients connected to therapists so we wanted to tackle this aspect early on as we build on features focusing on the therapist-client association |
| TOTAL SPRINT 2 SIZE |  | 39 |  |  |

6.2 Sprint 2 System Functionality

At the end of Sprint 2, the HealthQuest Wellness application will have the following functionality in addition to everything completed in Sprint 1:

Clients and therapists will be able to communicate directly through a real-time chat interface, with the conversation history stored and retrievable at any time. Therapists will have access to an organized chat page that lists all active conversations with clear timestamps and a visual distinction between client and colleague messages. Clients will be able to interact with the AI therapy chatbot through a dedicated chat page, with the AI responding in real time using mental health-appropriate language. The crisis detection system will be active, monitoring journal entries and chat messages for indicators of dangerous behavior. When a concern is detected, the client will be informed that their therapist has been notified, and the therapist will receive an immediate push notification with a link to the flagged content. Therapists will also be able to leave comments on client journal entries, with clients receiving a push notification when new feedback is available. The account deletion feature will be completed, allowing clients to deactivate their accounts while preserving data for therapist review. Finally, the therapist referral code system will be in place. Each therapist profile can auto-generate a unique code for each client, which they can enter at sign-up to link themselves to that therapist.

6.3 Dependencies and Risks

The most significant dependency in Sprint 2 is the AI model integration. User stories 13 (push notifications for crisis) and 14 (AI tracking for dangerous behavior) both depend on the AI service being operational before they can be fully tested end-to-end. If the AI provider decision is not finalized early in the sprint, these two user stories risk being partially implemented or untestable by the sprint's end. The team should treat finalizing the AI provider as the first priority of Sprint 2.

The therapist-client chat (ID 11) and the organized chat page (ID 16) are tightly coupled, as the chat page UI cannot be meaningfully tested until the chat functionality is working. Cameron and Lauren will coordinate closely and aim to have the backend chat infrastructure in place before the UI work begins.

User story 24 (therapist comments) carries partial implementation from Sprint 1. The database is designed for therapist comments, but features like push notification side were not completed, so the team should confirm exactly what remains before estimating time. If the notification infrastructure being built for story 13 can be reused here, that reduces risk significantly.

Sprint 2 is scoped at 39 points, which is 4 points above the team's Sprint 1 velocity of 28. This is a notable increase and carries a risk of not completing all stories. If the team falls behind mid-sprint, it’d be wise to put off low-risk user stories that don’t impact our ability to complete other stories.